Priority Home RISKS and CHALLENGES LOG Identification and Assessment

Date

| Risk # | Risk Description | Impact Insignificant Minor Moderate Major Extreme | Likelihood Rare Unlikely Possible Likely Almost Certain | Risk Level Low Moderate High Critical | Risk Trigger | Risk Response Plan | Responsibility | Target Date To Complete M/D/Y | Review Schedule M/D/Y | Risk Status Open Closed Escalated |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Resistance to the philosophy | Major | Likely | Critical | Apprehension on the part of hospital care providers to discharge patients home | Develop a robust communication and education plan detailing the philosophy, the benefits, and the implications on staff | Implementation Team Members, Educators | See B. Readiness to Implement (Priority Home Implementation Checklist) | Review schedule is based on the schedule for the implementation team meetings | Open |
| 2. | Sustaining the cultural shift | Major | Possible | High | Staff begin to shift away from the Priority Home philosophy and revert back to former processes and procedures | Continuously reinforce the Priority Home philosophy and supporting principles Monitor and share process metrics for Priority Home Monitor attendance at education sessions | Managers, Educators | See D. Evaluation & Sustainability (Priority Home Implementation Checklist) | Ongoing | Open |
| Distribution: | Lead |  |
|  | Executive Sponsor |  |

| Project Risk Type |
| --- |
| Business | Risks that may relate to the delivery of health care that includes internal and external factors impacting on the operations of the department. |
| Resource | Risks that relate to the resources used by the organization to accomplish its objectives. |
| Compliance | Risks that originate from the requirement to comply with a regulatory framework, policies, directives or legal agreements. |

| Project Risk Matrix |
| --- |
| Likelihood | Impact |
|  | Insignificant | Minor | Moderate | Major | Extreme |
| Almost Certain | Moderate Risk | Moderate Risk | High Risk | Critical Risk | Critical Risk |
| Likely | Low Risk | Moderate Risk | High Risk | Critical Risk | Critical Risk |
| Possible | Low Risk | Moderate Risk | Moderate Risk | High Risk | High Risk |
| Unlikely | Low Risk | Low Risk | Moderate Risk | Moderate Risk | High Risk |
| Rare | Low Risk | Low Risk | Low Risk | Moderate Risk | Moderate Risk |

| Risk Matrix Legend |
| --- |
| Risk Level | Action and Level of Involvement Required |
| Critical Risk | Inform Executive Sponsor Escalate to the Project Management Office Immediate Action is Required by Executive Sponsor and may involve WRHA Senior Management as appropriate |
| High Risk | Inform Executive Sponsor Escalate to the Project Management Office Executive Sponsor involvement/attention is essential to manage risks – provide update to WRHA Senior Management as appropriate |
| Moderate Risk | Inform Executive Sponsor Escalate to the Project Management Office Management mitigation and ongoing monitoring required Inform Project Sponsor |
| Low Risk | Resolve within the Project Team Accept, but monitor risks Manage by routine procedures within the Program, Site and Project |